## Summary
Phase 3 Test Execution
Metric | Result
Planned cases | 37
Final passed | 37
Final failed | 0
Final blocked | 0
Closed defects | 2
Final pass rate | 100%
Environment | Version | Scope | Result | Evidence | Notes
Brave on Windows 11 | 151.1.93.134 | Complete UI regression | 24 passed | pytest HTML/JUnit generated locally | No final failures
Chrome for Testing | 151.0.7922.77 | 320, 760, 1280 px | 3 passed | Focused responsive run | No horizontal overflow after correction
NVDA portable | 2026.1.1 | Names, structure, live feedback | Pass | Verified local screen-reader log | Success and alert feedback announced
Application build | React/FastAPI/SQLite | Corrected baseline | Pass | Production frontend build | Synthetic local data only

## Executions
Execution ID | Cycle ID | Test Case ID | Case Version | Attempt | Final Case Result | Executed At | Tester Role | Baseline | Environment | Execution Mode | Actual Result | Evidence | Linked Defect | Retest Disposition
PH3-20260810-001 | CYCLE-PH3-20260810 | TC-AUTH-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | A unique member account was created and the member workspace opened. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-002 | CYCLE-PH3-20260810 | TC-AUTH-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | The same normalized email in different letter case returned the conflict message and created no duplicate. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-003 | CYCLE-PH3-20260810 | TC-AUTH-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Valid credentials opened the correct member workspace. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-004 | CYCLE-PH3-20260810 | TC-AUTH-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | An incorrect password returned the neutral credential error and created no session. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-005 | CYCLE-PH3-20260810 | TC-AUTH-005 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | An unknown email returned the same neutral credential error and created no session. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-006 | CYCLE-PH3-20260810 | TC-AUTH-006 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Sign-out cleared the session; refresh remained on sign-in. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-007 | CYCLE-PH3-20260810 | TC-AUTH-007 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | An invalid token was cleared and the session-expired recovery message was shown. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-008 | CYCLE-PH3-20260810 | TC-PROFILE-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | The updated display name remained after sign-out and sign-in. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-009 | CYCLE-PH3-20260810 | TC-PROFILE-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Whitespace-only profile input was rejected and the stored name remained unchanged. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-010 | CYCLE-PH3-20260810 | TC-TASK-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | One owned task was created with the submitted title and description. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-011 | CYCLE-PH3-20260810 | TC-TASK-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Whitespace-only title input was rejected and no task was created. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-012 | CYCLE-PH3-20260810 | TC-TASK-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | A 120-character title and 1,000-character description were stored without truncation. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-013 | CYCLE-PH3-20260810 | TC-TASK-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | 121-character title and 1,001-character description requests returned validation errors and stored no extra task. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-014 | CYCLE-PH3-20260810 | TC-TASK-005 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Edited title and description remained after refresh. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-015 | CYCLE-PH3-20260810 | TC-TASK-006 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | The active task became completed and appeared under Completed. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-016 | CYCLE-PH3-20260810 | TC-TASK-007 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | The completed task reopened and appeared under Active. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-017 | CYCLE-PH3-20260810 | TC-TASK-008 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Canceling the delete confirmation preserved the task after refresh. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-018 | CYCLE-PH3-20260810 | TC-TASK-009 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Confirming deletion removed the task; search and refresh did not restore it. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-019 | CYCLE-PH3-20260810 | TC-SEARCH-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Title search matched regardless of letter case. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-020 | CYCLE-PH3-20260810 | TC-SEARCH-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | A description-only term returned the matching task. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-021 | CYCLE-PH3-20260810 | TC-SEARCH-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | A no-match term showed the empty state without an error. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-022 | CYCLE-PH3-20260810 | TC-SEARCH-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Active excluded the completed task. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-023 | CYCLE-PH3-20260810 | TC-SEARCH-005 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Completed excluded active tasks. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-024 | CYCLE-PH3-20260810 | TC-SEARCH-006 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Search and status constraints applied together. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-025 | CYCLE-PH3-20260810 | TC-SEARCH-007 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | All showed every owned task and no task from another member. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-026 | CYCLE-PH3-20260810 | TC-ADMIN-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Team view showed tasks with the correct owner names and emails. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-027 | CYCLE-PH3-20260810 | TC-ADMIN-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | Other-user tasks exposed no mutation controls and a direct update returned not found. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-028 | CYCLE-PH3-20260810 | TC-ADMIN-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | A member had no team-view control and the administrator endpoint returned forbidden. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-029 | CYCLE-PH3-20260810 | TC-ADMIN-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | My tasks showed only the administrator-owned task with edit controls. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-030 | CYCLE-PH3-20260810 | TC-AUTHZ-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | Two members each received only their own task records. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-031 | CYCLE-PH3-20260810 | TC-ACCESS-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted manual | Keyboard focus reached and operated create, profile, filter, complete, delete, and sign-out controls with visible focus. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-032 | CYCLE-PH3-20260810 | TC-ACCESS-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134; NVDA 2026.1.1 portable | Browser-assisted manual | Controls exposed names and logical structure; the screen reader announced success and validation feedback. | tests/ui/test_phase3_catalog.py; verified portable screen-reader log with success and alert announcements |  | Not required
PH3-20260810-033 | CYCLE-PH3-20260810 | TC-ACCESS-003 | v1.0 | Initial | Fail | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Manual measurement | Input border measured 2.00:1 against white and the focus outline measured 2.03:1 against white. | Computed-style contrast measurement | DEF-P3-001 | Corrected and queued for focused retest
PH3-20260810-034 | CYCLE-PH3-20260810 | TC-ACCESS-003 | v1.0 | Retest | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted manual | Text, border, and dual-ring focus measurements met the applicable project contrast targets after correction. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed | DEF-P3-001 | Focused retest and full Brave regression passed
PH3-20260810-035 | CYCLE-PH3-20260810 | TC-COMPAT-001 | v1.0 | Initial | Fail | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Chrome for Testing 151.0.7922.77 | Browser-assisted compatibility | At 320 pixels the document width exceeded the viewport because of the page minimum width and competing header layout. | tests/ui/test_phase3_catalog.py focused Chrome run | DEF-P3-002 | Corrected and queued for focused retest
PH3-20260810-036 | CYCLE-PH3-20260810 | TC-COMPAT-001 | v1.0 | Retest | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Chrome for Testing 151.0.7922.77 | Browser-assisted recovery/compatibility | Core controls remained visible and operable with no horizontal overflow at 320, 760, and 1,280 pixels after correction. | tests/ui/test_phase3_catalog.py; Chrome responsive run: 3 passed | DEF-P3-002 | Focused retest and full Brave regression passed
PH3-20260810-037 | CYCLE-PH3-20260810 | TC-REMOTE-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted recovery/compatibility | Refresh preserved the valid session and retained exactly one copy of the created task. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-038 | CYCLE-PH3-20260810 | TC-REMOTE-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted recovery/compatibility | A blocked API mutation showed an error, no success, and no stored task; reconnection preserved the member role. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-039 | CYCLE-PH3-20260810 | TC-USABILITY-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted manual | Action labels and feedback were clear; deletion named the task and required explicit confirmation. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required

## Defects
Defect ID | Title | Severity | Status | Detected By | Initial Result | Correction | Retest Evidence
DEF-P3-001 | Component and focus contrast below target | High | Closed | TC-ACCESS-003 | 2.00:1 input border; 2.03:1 focus outline against white | Darkened field borders and added a white plus navy dual focus ring | Focused accessibility retest passed; complete Brave run 24 passed
DEF-P3-002 | Horizontal overflow at 320 pixels | High | Closed | TC-COMPAT-001 | Document width exceeded the 320-pixel viewport | Removed the page minimum width and stacked the narrow header | Chrome 320, 760, and 1280 runs passed