## Test Cycles
Cycle ID | Name | Sprint | Purpose | Scope | Baseline | Environment | Execution Mode | Planned Tests | Passed | Failed | Blocked | Not Run | Status | Release Decision | Evidence
CYCLE-PH3-20260810 | Phase 3 functional acceptance | Sprint 1 | Validate approved functional, accessibility, compatibility, reliability, and usability cases. | 37 approved cases; 39 attempts including two retests | Local corrected baseline | Windows 11; Brave 151.1.93.134; Chrome for Testing 151.0.7922.77; NVDA 2026.1.1 portable | Automated and browser-assisted manual | 37 | 37 | 0 | 0 | 0 | Completed | Functional baseline accepted after retest | test-management/TEST_EXECUTIONS.csv; test-management/PHASE_3_EXECUTION_REGISTER.xlsx
CYCLE-PH5-REGRESSION-20260810 | Phase 5 critical UI regression | Sprint 2 | Detect unintended change in stable critical member and administrator workflows. | Six tests selected by the regression marker | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI | 6 | 6 | 0 | 0 | 0 | Completed | Continue broader testing | reports/pytest-report.html; README.md#functional-and-regression-automation
CYCLE-PH6-API-20260810 | Phase 6 API contracts and authorization | Sprint 2 | Validate REST contracts, negative paths, CRUD, authorization, and controlled server error handling. | Complete API suite | Isolated in-process application | Windows 11; Python 3.12 | Automated API | 24 | 24 | 0 | 0 | 0 | Completed | No API blocker | tests/api/test_workboard_api.py; README.md#api-testing
CYCLE-PH7-DATABASE-20260810 | Phase 7 database integrity | Sprint 2 | Validate schema, constraints, persistence, ownership, and API-to-SQL consistency. | Complete database suite | New temporary SQLite database per test | Windows 11; Python 3.12; SQLite | Automated database | 16 | 16 | 0 | 0 | 0 | Completed | No database blocker | tests/database/test_workboard_database.py; README.md#database-testing
CYCLE-PH8-ACCESSIBILITY-20260810 | Phase 8 accessibility assessment | Sprint 3 | Combine automated rules with keyboard, Lighthouse, WAVE, and NVDA assessment. | Ten automated tests plus recorded manual and tool-assisted checks | Local corrected baseline and controlled local defect baseline | Windows 11; Brave 151.1.93.134; NVDA 2026.1.1 portable | Automated and manual | 10 | 10 | 0 | 0 | 0 | Completed | No open confirmed finding in tested scope | accessibility/ACCESSIBILITY_TEST_PLAN.md; accessibility/FINDINGS.md; accessibility/REMEDIATION_RETEST.md
CYCLE-PH9-MANAGEMENT-20260810 | Phase 9 management integrity | Sprint 3 | Validate IDs, links, cycle counts, defect/retest chains, and required management artifacts. | Complete management-artifact validation suite | Repository checkpoint candidate | Windows 11; Python 3.12 | Automated artifact validation | 8 | 8 | 0 | 0 | 0 | Completed | Phase 9 checkpoint ready; continue after approval | tests/test_management/test_agile_artifacts.py: 8 passed; complete project regression: 82 passed
CYCLE-PH10-PERFORMANCE | Phase 10 local performance baseline | Sprint 4 | Evaluate the bounded local performance target. | NFR-PERF-001 | Not established | Local environment to be recorded in Phase 10 | Planned | 1 | 0 | 0 | 0 | 1 | Planned | Not evaluated | Phase 10
CYCLE-PH11-UAT | Phase 11 simulated UAT | Sprint 4 | Record stakeholder-oriented acceptance results without implying client delivery. | Approved simulated UAT scenarios | Not established | Local environment to be recorded in Phase 11 | Planned | 0 | 0 | 0 | 0 | 0 | Planned | Not evaluated | Phase 11

## Executions
Execution ID | Cycle ID | Test Case ID | Case Version | Attempt | Final Case Result | Executed At | Tester Role | Baseline | Environment | Execution Mode | Actual Result | Evidence | Linked Defect | Retest Disposition
PH3-20260810-001 | CYCLE-PH3-20260810 | TC-AUTH-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | A unique member account was created and the member workspace opened. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-002 | CYCLE-PH3-20260810 | TC-AUTH-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | The same normalized email in different letter case returned the conflict message and created no duplicate. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-003 | CYCLE-PH3-20260810 | TC-AUTH-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Valid credentials opened the correct member workspace. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-004 | CYCLE-PH3-20260810 | TC-AUTH-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | An incorrect password returned the neutral credential error and created no session. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-005 | CYCLE-PH3-20260810 | TC-AUTH-005 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | An unknown email returned the same neutral credential error and created no session. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-006 | CYCLE-PH3-20260810 | TC-AUTH-006 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Sign-out cleared the session; refresh remained on sign-in. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-007 | CYCLE-PH3-20260810 | TC-AUTH-007 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | An invalid token was cleared and the session-expired recovery message was shown. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-008 | CYCLE-PH3-20260810 | TC-PROFILE-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | The updated display name remained after sign-out and sign-in. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-009 | CYCLE-PH3-20260810 | TC-PROFILE-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Whitespace-only profile input was rejected and the stored name remained unchanged. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-010 | CYCLE-PH3-20260810 | TC-TASK-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | One owned task was created with the submitted title and description. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-011 | CYCLE-PH3-20260810 | TC-TASK-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Whitespace-only title input was rejected and no task was created. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-012 | CYCLE-PH3-20260810 | TC-TASK-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | A 120-character title and 1,000-character description were stored without truncation. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-013 | CYCLE-PH3-20260810 | TC-TASK-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | 121-character title and 1,001-character description requests returned validation errors and stored no extra task. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-014 | CYCLE-PH3-20260810 | TC-TASK-005 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Edited title and description remained after refresh. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-015 | CYCLE-PH3-20260810 | TC-TASK-006 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | The active task became completed and appeared under Completed. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-016 | CYCLE-PH3-20260810 | TC-TASK-007 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | The completed task reopened and appeared under Active. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-017 | CYCLE-PH3-20260810 | TC-TASK-008 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Canceling the delete confirmation preserved the task after refresh. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-018 | CYCLE-PH3-20260810 | TC-TASK-009 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Confirming deletion removed the task; search and refresh did not restore it. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-019 | CYCLE-PH3-20260810 | TC-SEARCH-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Title search matched regardless of letter case. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-020 | CYCLE-PH3-20260810 | TC-SEARCH-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | A description-only term returned the matching task. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-021 | CYCLE-PH3-20260810 | TC-SEARCH-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | A no-match term showed the empty state without an error. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-022 | CYCLE-PH3-20260810 | TC-SEARCH-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Active excluded the completed task. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-023 | CYCLE-PH3-20260810 | TC-SEARCH-005 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Completed excluded active tasks. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-024 | CYCLE-PH3-20260810 | TC-SEARCH-006 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Search and status constraints applied together. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-025 | CYCLE-PH3-20260810 | TC-SEARCH-007 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | All showed every owned task and no task from another member. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-026 | CYCLE-PH3-20260810 | TC-ADMIN-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | Team view showed tasks with the correct owner names and emails. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-027 | CYCLE-PH3-20260810 | TC-ADMIN-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | Other-user tasks exposed no mutation controls and a direct update returned not found. | tests/ui/test_functional_regression.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-028 | CYCLE-PH3-20260810 | TC-ADMIN-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | A member had no team-view control and the administrator endpoint returned forbidden. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-029 | CYCLE-PH3-20260810 | TC-ADMIN-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI execution | My tasks showed only the administrator-owned task with edit controls. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-030 | CYCLE-PH3-20260810 | TC-AUTHZ-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | UI and API assisted | Two members each received only their own task records. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-031 | CYCLE-PH3-20260810 | TC-ACCESS-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted manual | Keyboard focus reached and operated create, profile, filter, complete, delete, and sign-out controls with visible focus. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-032 | CYCLE-PH3-20260810 | TC-ACCESS-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134; NVDA 2026.1.1 portable | Browser-assisted manual | Controls exposed names and logical structure; the screen reader announced success and validation feedback. | tests/ui/test_phase3_catalog.py; verified portable screen-reader log with success and alert announcements |  | Not required
PH3-20260810-033 | CYCLE-PH3-20260810 | TC-ACCESS-003 | v1.0 | Initial | Fail | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Manual measurement | Input border measured 2.00:1 against white and the focus outline measured 2.03:1 against white. | Computed-style contrast measurement | DEF-P3-001 | Corrected and queued for focused retest
PH3-20260810-034 | CYCLE-PH3-20260810 | TC-ACCESS-003 | v1.0 | Retest | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted manual | Text, border, and dual-ring focus measurements met the applicable project contrast targets after correction. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed | DEF-P3-001 | Focused retest and full Brave regression passed
PH3-20260810-035 | CYCLE-PH3-20260810 | TC-COMPAT-001 | v1.0 | Initial | Fail | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Chrome for Testing 151.0.7922.77 | Browser-assisted compatibility | At 320 pixels the document width exceeded the viewport because of the page minimum width and competing header layout. | tests/ui/test_phase3_catalog.py focused Chrome run | DEF-P3-002 | Corrected and queued for focused retest
PH3-20260810-036 | CYCLE-PH3-20260810 | TC-COMPAT-001 | v1.0 | Retest | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Chrome for Testing 151.0.7922.77 | Browser-assisted recovery/compatibility | Core controls remained visible and operable with no horizontal overflow at 320, 760, and 1,280 pixels after correction. | tests/ui/test_phase3_catalog.py; Chrome responsive run: 3 passed | DEF-P3-002 | Focused retest and full Brave regression passed
PH3-20260810-037 | CYCLE-PH3-20260810 | TC-REMOTE-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted recovery/compatibility | Refresh preserved the valid session and retained exactly one copy of the created task. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-038 | CYCLE-PH3-20260810 | TC-REMOTE-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted recovery/compatibility | A blocked API mutation showed an error, no success, and no stored task; reconnection preserved the member role. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH3-20260810-039 | CYCLE-PH3-20260810 | TC-USABILITY-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Browser-assisted manual | Action labels and feedback were clear; deletion named the task and required explicit confirmation. | tests/ui/test_phase3_catalog.py; complete Brave run: 24 passed |  | Not required
PH5-20260810-001 | CYCLE-PH5-REGRESSION-20260810 | TC-AUTH-004 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI | Incorrect credentials created no session. | tests/ui/test_functional_regression.py::test_incorrect_password_does_not_create_session; regression cycle: 6 passed |  | Not required
PH5-20260810-002 | CYCLE-PH5-REGRESSION-20260810 | TC-TASK-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI | The member task lifecycle completed successfully. | tests/ui/test_functional_regression.py::test_member_task_lifecycle; regression cycle: 6 passed |  | Not required
PH5-20260810-003 | CYCLE-PH5-REGRESSION-20260810 | TC-TASK-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI | A blank task title was rejected. | tests/ui/test_functional_regression.py::test_blank_task_title_is_rejected; regression cycle: 6 passed |  | Not required
PH5-20260810-004 | CYCLE-PH5-REGRESSION-20260810 | TC-SEARCH-006 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI | Search and state filters applied together. | tests/ui/test_functional_regression.py::test_search_and_status_filter_apply_together; regression cycle: 6 passed |  | Not required
PH5-20260810-005 | CYCLE-PH5-REGRESSION-20260810 | TC-PROFILE-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI | The updated display name persisted across sessions. | tests/ui/test_functional_regression.py::test_profile_name_persists_across_sessions; regression cycle: 6 passed |  | Not required
PH5-20260810-006 | CYCLE-PH5-REGRESSION-20260810 | TC-ADMIN-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134 | Automated UI | The administrator team view remained read-only for another member's task. | tests/ui/test_functional_regression.py::test_administrator_team_view_is_read_only_for_member_task; regression cycle: 6 passed |  | Not required
PH6-20260810-001 | CYCLE-PH6-API-20260810 | TC-API-AUTH-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Isolated in-process application | Windows 11; Python 3.12 | Automated API | Missing and invalid tokens returned 401 without protected data. | tests/api/test_workboard_api.py::test_protected_endpoint_rejects_missing_or_invalid_token; API cycle: 24 passed |  | Not required
PH6-20260810-002 | CYCLE-PH6-API-20260810 | TC-API-AUTHZ-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Isolated in-process application | Windows 11; Python 3.12 | Automated API | Another member's update request returned 404. | tests/api/test_workboard_api.py::test_member_cannot_mutate_another_members_task; API cycle: 24 passed |  | Not required
PH6-20260810-003 | CYCLE-PH6-API-20260810 | TC-API-AUTHZ-002 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Isolated in-process application | Windows 11; Python 3.12 | Automated API | Another member's delete request returned 404. | tests/api/test_workboard_api.py::test_member_cannot_mutate_another_members_task; API cycle: 24 passed |  | Not required
PH6-20260810-004 | CYCLE-PH6-API-20260810 | TC-API-AUTHZ-003 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Isolated in-process application | Windows 11; Python 3.12 | Automated API | Unauthenticated task access returned 401 without task data. | tests/api/test_workboard_api.py::test_protected_endpoint_rejects_missing_or_invalid_token; API cycle: 24 passed |  | Not required
PH7-20260810-001 | CYCLE-PH7-DATABASE-20260810 | TC-DB-AUTH-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | New temporary SQLite database per test | Windows 11; Python 3.12; SQLite | Automated database | Registration stored a verifiable salted hash rather than the submitted password. | tests/database/test_workboard_database.py::test_registration_persists_normalized_user_and_salted_hash; database cycle: 16 passed |  | Not required
PH7-20260810-002 | CYCLE-PH7-DATABASE-20260810 | TC-DB-AUTHZ-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | New temporary SQLite database per test | Windows 11; Python 3.12; SQLite | Automated database | Rejected update and delete requests left row values and counts unchanged. | tests/database/test_workboard_database.py::test_unauthorized_update_and_delete_leave_database_unchanged; database cycle: 16 passed |  | Not required
PH8-20260810-001 | CYCLE-PH8-ACCESSIBILITY-20260810 | TC-ACCESS-002 | v1.0 | Retest | Pass | 2026-08-10 | Test engineer | Local corrected baseline | Windows 11; Brave 151.1.93.134; NVDA 2026.1.1 portable | Automated and manual | Corrected names, structure, and live feedback passed the dedicated suite and recorded manual retests. | tests/accessibility/test_accessibility.py; accessibility cycle: 10 passed; accessibility/REMEDIATION_RETEST.md | DEF-P8-001; DEF-P8-002 | Focused tool-assisted retests and complete accessibility suite passed
PH9-20260810-001 | CYCLE-PH9-MANAGEMENT-20260810 | TC-RELEASE-001 | v1.0 | Initial | Pass | 2026-08-10 | Test engineer | Repository checkpoint candidate | Windows 11; Python 3.12; Brave 151.1.93.134 | Automated artifact validation | All required artifacts, IDs, case and cycle links, acceptance coverage, defect/retest chains, and tool mappings passed validation. | tests/test_management/test_agile_artifacts.py: 8 passed; complete project regression: 82 passed |  | Not required

## Traceability
Requirement ID | User Story ID | Acceptance Criteria ID | Test Case ID | Automated Test | Test Cycle ID | Execution ID | Execution Status | Defect ID | Retest Status | Final Status
FR-AUTH-001 | US-001 | AC-US001-01 | TC-AUTH-001 | tests/ui/test_functional_regression.py::test_member_can_register_and_sign_out | CYCLE-PH3-20260810 | PH3-20260810-001 | Pass |  | Not required | Covered
FR-AUTH-003 | US-002 | AC-US002-02 | TC-API-AUTH-001 | tests/api/test_workboard_api.py::test_protected_endpoint_rejects_missing_or_invalid_token | CYCLE-PH6-API-20260810 | PH6-20260810-001 | Pass |  | Not required | Covered
FR-TASK-001 | US-003 | AC-US003-01 | TC-TASK-001 | tests/ui/test_functional_regression.py::test_member_task_lifecycle | CYCLE-PH3-20260810 | PH3-20260810-010 | Pass |  | Not required | Covered
FR-TASK-006 | US-004 | AC-US004-05 | TC-SEARCH-006 | tests/ui/test_functional_regression.py::test_search_and_status_filter_apply_together | CYCLE-PH5-REGRESSION-20260810 | PH5-20260810-004 | Pass |  | Not required | Covered
FR-PROFILE-001 | US-005 | AC-US005-03 | TC-PROFILE-001 | tests/ui/test_functional_regression.py::test_profile_name_persists_across_sessions | CYCLE-PH5-REGRESSION-20260810 | PH5-20260810-005 | Pass |  | Not required | Covered
FR-ADMIN-002 | US-006 | AC-US006-02 | TC-ADMIN-002 | tests/ui/test_functional_regression.py::test_administrator_team_view_is_read_only_for_member_task | CYCLE-PH5-REGRESSION-20260810 | PH5-20260810-006 | Pass |  | Not required | Covered
FR-AUTHZ-001 | US-007 | AC-US007-05 | TC-DB-AUTHZ-001 | tests/database/test_workboard_database.py::test_unauthorized_update_and_delete_leave_database_unchanged | CYCLE-PH7-DATABASE-20260810 | PH7-20260810-002 | Pass |  | Not required | Covered
NFR-ACC-004 | US-008 | AC-US008-06 | TC-ACCESS-003 | tests/ui/test_phase3_catalog.py::test_component_and_text_contrast | CYCLE-PH3-20260810 | PH3-20260810-034 | Pass after retest | DEF-P3-001 | Passed | Covered; defect closed
NFR-REMOTE-001 | US-009 | AC-US009-03 | TC-REMOTE-002 | tests/ui/test_phase3_catalog.py::test_connection_interruption_has_no_false_success | CYCLE-PH3-20260810 | PH3-20260810-038 | Pass |  | Not required | Covered
BR-004 | US-010 | AC-US010-01 | TC-RELEASE-001 | tests/test_management/test_agile_artifacts.py | CYCLE-PH9-MANAGEMENT-20260810 | PH9-20260810-001 | Pass |  | Not required | Covered at Phase 9 checkpoint

## Test Cases
Test Case ID | Title | Objective | Type | Priority | Requirement IDs | Acceptance Criteria IDs | Preconditions | Test Data | Steps | Expected Result | Labels | Automation Candidate | Case Status | Version
TC-AUTH-001 | Register with valid synthetic account | Confirm a visitor can create a member account. | Smoke | Critical | FR-AUTH-001; NFR-DATA-001 | AC-US001-01 | Visitor is signed out; email is not registered. | new.member@example.test; SyntheticPass123 | 1. Open registration. 2. Enter a synthetic display name, unique email, and valid password. 3. Submit. | One member account is created, the workspace opens, and the header shows the new member. | auth; smoke; positive | Yes | Approved | v1.0
TC-AUTH-002 | Reject duplicate email registration | Confirm normalized email uniqueness is enforced. | Negative | High | FR-AUTH-001 | AC-US001-02 | A synthetic member account already exists. | Existing email with changed letter case | 1. Sign out. 2. Open registration. 3. Submit the existing email with different letter case and otherwise valid data. | Registration is rejected with a conflict message and no second account is created. | auth; negative; regression | Yes | Approved | v1.0
TC-AUTH-003 | Sign in with valid credentials | Confirm a registered user can start an authenticated session. | Smoke | Critical | FR-AUTH-002 | AC-US001-03 | Synthetic member account exists; user is signed out. | Valid member email and password | 1. Open sign-in. 2. Enter valid credentials. 3. Submit. | The workspace opens and identifies the correct display name and role. | auth; smoke; positive | Yes | Approved | v1.0
TC-AUTH-004 | Reject incorrect password | Confirm incorrect credentials do not create a session. | Negative | Critical | FR-AUTH-002 | AC-US001-04 | Synthetic member account exists; user is signed out. | Valid email; incorrect synthetic password | 1. Enter the registered email and an incorrect password. 2. Submit. | Access is denied with a clear credential error and the sign-in page remains displayed. | auth; negative; security | Yes | Approved | v1.0
TC-AUTH-005 | Reject unknown email | Confirm an unknown identity receives the same credential error. | Negative | High | FR-AUTH-002 | AC-US001-04 | User is signed out. | unknown.user@example.test; valid-format password | 1. Enter an unregistered email and valid-format password. 2. Submit. | Access is denied without revealing whether the email exists. | auth; negative; security | Yes | Approved | v1.0
TC-AUTH-006 | Sign out from workspace | Confirm sign-out removes the current browser session. | Smoke | Critical | FR-AUTH-003 | AC-US002-01 | Member is signed in. | Authenticated member | 1. Select Sign out. 2. Attempt to return to the workspace by refreshing the page. | The sign-in page appears and the workspace does not reopen without credentials. | auth; smoke; session | Yes | Approved | v1.0
TC-AUTH-007 | Recover from invalidated session | Confirm stale local session data does not leave a misleading signed-in state. | Recovery | High | FR-AUTH-003; NFR-REL-001 | AC-US002-03; AC-US009-02 | Member is signed in; local-only backend can be restarted safely. | Authenticated local session | 1. Restart the backend so the local signing key changes. 2. Refresh the workspace. | The stale session is cleared and sign-in is shown with an understandable recovery message. | auth; recovery; regression | Partial | Approved | v1.0
TC-PROFILE-001 | Update profile name and verify persistence | Confirm a valid display-name change persists across sessions. | Functional | High | FR-PROFILE-001 | AC-US005-01; AC-US005-02; AC-US005-03 | Member is signed in. | Updated Member | 1. Change the profile display name. 2. Save. 3. Confirm the header changes. 4. Sign out and sign back in. | A success message appears and the updated name remains after the new login. | profile; positive; regression | Yes | Approved | v1.0
TC-PROFILE-002 | Reject blank profile name | Confirm blank display names cannot replace a stored name. | Negative | Medium | FR-PROFILE-001 | AC-US005-04 | Member is signed in and has a known display name. | Whitespace-only name | 1. Replace the profile name with spaces. 2. Attempt to save. | Validation rejects the value and the prior name remains stored. | profile; negative; validation | Yes | Approved | v1.0
TC-TASK-001 | Create task with valid values | Confirm a member can create and view an owned task. | Smoke | Critical | FR-TASK-001; FR-TASK-002 | AC-US003-01 | Member is signed in; target title is unique. | Title: Review sprint checklist; Description: Synthetic task | 1. Enter a valid title and description. 2. Select Add task. | One new active task appears with the submitted values and a creation message. | task; smoke; create | Yes | Approved | v1.0
TC-TASK-002 | Reject blank task title | Confirm a task cannot be created with a blank or whitespace title. | Negative | High | FR-TASK-001 | AC-US003-02 | Member is signed in. | Whitespace-only title | 1. Enter spaces as the title. 2. Enter an optional description. 3. Attempt to submit. | Validation prevents creation and no blank task appears. | task; negative; validation | Yes | Approved | v1.0
TC-TASK-003 | Accept task field boundaries | Confirm maximum allowed title and description lengths are accepted. | Boundary | Medium | FR-TASK-001 | AC-US003-03 | Member is signed in. | 120-character title; 1,000-character description | 1. Enter values exactly at both maximum lengths. 2. Submit. | The task is created and stored without truncation. | task; boundary; validation | Yes | Approved | v1.0
TC-TASK-004 | Reject task values over boundaries | Confirm values above allowed lengths are rejected. | Boundary | High | FR-TASK-001 | AC-US003-03 | Member is signed in. | 121-character title or 1,001-character description | 1. Attempt creation with a title one character over the limit. 2. Repeat with a description one character over the limit. | Each invalid submission is rejected and no overlength value is stored. | task; boundary; negative | Yes | Approved | v1.0
TC-TASK-005 | Edit owned task | Confirm valid title and description edits persist. | Functional | High | FR-TASK-003 | AC-US003-04 | Member owns an existing task. | Updated title and description | 1. Select Edit on the owned task. 2. Change both fields. 3. Confirm the edit. 4. Refresh the page. | The updated values appear immediately and remain after refresh. | task; update; regression | Yes | Approved | v1.0
TC-TASK-006 | Complete active task | Confirm an active task can be completed. | Smoke | Critical | FR-TASK-004 | AC-US003-05 | Member owns an active task. | Active task | 1. Select Complete. 2. View the Completed filter. | The task is visibly completed, a success message appears, and the task is included under Completed. | task; state; smoke | Yes | Approved | v1.0
TC-TASK-007 | Reopen completed task | Confirm a completed task can return to active state. | Functional | High | FR-TASK-004 | AC-US003-06 | Member owns a completed task. | Completed task | 1. Select Reopen. 2. View the Active filter. | The task is active, a success message appears, and the task is included under Active. | task; state; regression | Yes | Approved | v1.0
TC-TASK-008 | Cancel task deletion | Confirm canceling the destructive action preserves the task. | Functional | Medium | FR-TASK-005 | AC-US003-07 | Member owns a task. | Owned task | 1. Select Delete. 2. Cancel the confirmation. 3. Refresh the page. | The task remains present and unchanged. | task; delete; usability | Partial | Approved | v1.0
TC-TASK-009 | Confirm task deletion | Confirm an owned task can be deleted after confirmation. | Functional | Critical | FR-TASK-005 | AC-US003-08; AC-US003-09 | Member owns a disposable synthetic task. | Disposable task | 1. Select Delete. 2. Confirm the action. 3. Search for the deleted title. 4. Refresh the page. | The task remains absent and a clear deletion message is shown. | task; delete; regression | Yes | Approved | v1.0
TC-SEARCH-001 | Search task title case-insensitively | Confirm title search returns matching owned tasks regardless of case. | Functional | High | FR-TASK-006 | AC-US004-01 | Member owns tasks with distinct titles. | Search term using different letter case | 1. Enter a partial title with different letter case. 2. Review results. | Only owned tasks with matching titles or descriptions appear. | search; positive; regression | Yes | Approved | v1.0
TC-SEARCH-002 | Search task description | Confirm description text participates in search. | Functional | Medium | FR-TASK-006 | AC-US004-01 | Member owns a task with a unique description term. | Unique description term | 1. Search for the unique description term. | The matching task appears even when its title does not contain the term. | search; description | Yes | Approved | v1.0
TC-SEARCH-003 | Show empty state for no matches | Confirm no-match search is understandable and not treated as an error. | Usability | Medium | FR-TASK-006 | AC-US004-02 | Member is signed in. | Term that matches no task | 1. Search for a nonexistent term. | No task cards appear and the empty-state message is displayed without an error. | search; empty-state; usability | Yes | Approved | v1.0
TC-SEARCH-004 | Filter active tasks | Confirm Active excludes completed tasks. | Functional | High | FR-TASK-006 | AC-US004-03 | Member owns at least one active and one completed task. | Mixed task states | 1. Clear search. 2. Select Active. | Every displayed task is active and completed tasks are absent. | filter; active; regression | Yes | Approved | v1.0
TC-SEARCH-005 | Filter completed tasks | Confirm Completed excludes active tasks. | Functional | High | FR-TASK-006 | AC-US004-04 | Member owns at least one active and one completed task. | Mixed task states | 1. Clear search. 2. Select Completed. | Every displayed task is completed and active tasks are absent. | filter; completed; regression | Yes | Approved | v1.0
TC-SEARCH-006 | Combine search and status filter | Confirm every result satisfies both search and status conditions. | Regression | Critical | FR-TASK-006 | AC-US004-05 | Member owns matching active and completed tasks plus nonmatching tasks. | Shared search term; Active then Completed | 1. Enter the shared term. 2. Select Active and record results. 3. Select Completed and record results. | Each result matches the term and the selected state; no task from the opposite state appears. | filter; search; controlled-defect | Yes | Approved | v1.0
TC-SEARCH-007 | Display all owned tasks | Confirm All with no search returns the complete personal list. | Functional | Medium | FR-TASK-006 | AC-US004-06 | Member owns multiple tasks. | Known count of owned tasks | 1. Clear search. 2. Select All. 3. Compare displayed tasks with the known personal list. | Every owned task appears once and no other user task appears. | filter; all; regression | Yes | Approved | v1.0
TC-ADMIN-001 | Administrator views team tasks | Confirm team oversight includes owner identification for all users. | Functional | Critical | FR-ADMIN-001 | AC-US006-01 | Administrator and at least two members exist with tasks. | Synthetic administrator and member tasks | 1. Sign in as administrator. 2. Select All users tasks. 3. Review owners and records. | Tasks from each user appear with the correct owner name and email. | admin; oversight; regression | Yes | Approved | v1.0
TC-ADMIN-002 | Other-user tasks are read-only in team view | Confirm administrator UI does not offer mutations for another user task. | Authorization | Critical | FR-ADMIN-002; FR-AUTHZ-001 | AC-US006-02; AC-US006-03 | Administrator is in team view and another user owns a task. | Other-user task | 1. Locate another user task. 2. Inspect available actions. 3. Attempt direct member-route update using the task ID. | No mutation controls appear, the direct request is rejected, and the task remains unchanged. | admin; authorization; negative | Partial | Approved | v1.0
TC-ADMIN-003 | Member cannot access team oversight | Confirm team oversight is not available to a member. | Authorization | Critical | FR-ADMIN-001; FR-AUTHZ-001 | AC-US006-04 | Member is signed in. | Authenticated member | 1. Confirm no team-view control is displayed. 2. Request the administrator task endpoint with the member token. | The UI offers no team view and the endpoint returns 403 without team data. | admin; authorization; negative | Partial | Approved | v1.0
TC-ADMIN-004 | Administrator returns to personal task view | Confirm the administrator can isolate and manage only their own tasks. | Functional | High | FR-ADMIN-001; FR-AUTHZ-001 | AC-US006-05 | Administrator and another user each own a uniquely named task. | Administrator-owned and other-user tasks | 1. Sign in as administrator. 2. Select My tasks. 3. Compare the list with known ownership. 4. Edit the administrator-owned task. | Only administrator-owned tasks appear and the administrator can edit their own task. | admin; ownership; regression | Yes | Approved | v1.0
TC-AUTHZ-001 | Members see only their own tasks | Confirm task-list isolation between two member accounts. | Authorization | Critical | FR-AUTHZ-001 | AC-US007-01 | Two members each own uniquely named tasks. | member.one@example.test; member.two@example.test | 1. Sign in as member one and record visible tasks. 2. Sign out. 3. Sign in as member two and record visible tasks. | Each member sees only their own tasks and neither list exposes the other member record. | ownership; authorization; regression | Yes | Approved | v1.0
TC-ACCESS-001 | Complete core workflow with keyboard only | Confirm critical controls are reachable, operable, ordered, and visibly focused. | Accessibility | Critical | NFR-ACC-001; NFR-ACC-004 | AC-US008-01; AC-US008-02 | Corrected baseline is running; mouse is not used. | Synthetic account and disposable task | 1. Register or sign in using keyboard only. 2. Create, complete, filter, and delete a task. 3. Update the profile. 4. Sign out. | Every required control is reached in a logical order, activates from the keyboard, and shows visible focus. | accessibility; keyboard; manual | No | Approved | v1.0
TC-ACCESS-002 | Review names, feedback, and page structure | Confirm controls, messages, headings, and regions expose understandable semantics. | Accessibility | Critical | NFR-ACC-002; NFR-ACC-003; NFR-ACC-005 | AC-US008-03; AC-US008-04; AC-US008-05; AC-US008-07 | Corrected baseline is running; NVDA is available. | Valid and invalid form actions | 1. Review controls and headings with NVDA. 2. Trigger a validation error. 3. Complete a successful action. 4. Record announcements and structure. | Controls have descriptive names, page structure is logical, and new error and success messages are announced. | accessibility; NVDA; manual | No | Approved | v1.0
TC-ACCESS-003 | Measure text and component contrast | Confirm applicable foreground, background, focus, and component colors meet project targets. | Accessibility | High | NFR-ACC-004 | AC-US008-02; AC-US008-06 | Corrected baseline is running; contrast measurement tool is available. | Representative normal, hover, error, success, and focus states | 1. Identify text and interactive color pairs. 2. Measure normal and focus states. 3. Record ratios and applicable thresholds. | Each applicable pair meets its WCAG 2.2 AA project target or is recorded as a finding. | accessibility; contrast; manual | No | Approved | v1.0
TC-COMPAT-001 | Review responsive core workflows | Confirm required content remains usable at narrow and desktop widths. | Compatibility | High | NFR-COMPAT-001 | AC-US008-08 | Current stable Chrome is available. | Viewport widths: 320, 760, 1280 pixels | 1. At each target width, sign in and review task creation, filters, task actions, profile, and sign-out. 2. Check for clipping and unintended horizontal scrolling. | Content is readable and required controls remain visible and operable at each width. | responsive; Chrome; manual | Partial | Approved | v1.0
TC-REMOTE-001 | Refresh valid session without repeating action | Confirm refresh preserves a valid session and does not repeat the last mutation. | Recovery | High | NFR-REL-001; NFR-REMOTE-001 | AC-US002-04; AC-US009-01 | Member has a valid session and just created one uniquely named task. | Single uniquely named task | 1. Record the task count. 2. Refresh the page. 3. Recheck session, task count, and task state. | The member remains signed in, the task appears once, and no mutation is repeated. | remote; refresh; reliability | Yes | Approved | v1.0
TC-REMOTE-002 | Recover from simulated connection interruption | Confirm failure and reconnection do not change authorization or falsely report success. | Recovery | High | NFR-REMOTE-001 | AC-US009-03; AC-US009-04 | Member is signed in; local backend can be paused safely. | Disposable task mutation | 1. Pause the local backend. 2. Attempt one task mutation. 3. Record feedback. 4. Restore the backend and sign in if required. 5. Verify task and role state. | No false success is shown; after recovery, authorization is unchanged and the task reflects only confirmed operations. | remote; interruption; reliability | Partial | Approved | v1.0
TC-USABILITY-001 | Review action feedback and destructive clarity | Confirm common actions communicate outcome and deletion is clearly distinguished. | Usability | Medium | FR-TASK-005; NFR-ACC-003 | AC-US003-07; AC-US003-09 | Member is signed in with a disposable task. | Create, update, complete, reopen, cancel delete, confirm delete | 1. Perform each listed action in sequence. 2. Observe labels, messages, and confirmation wording. 3. Note confusion separately from requirement failures. | Each action has understandable wording and feedback, and deletion requires explicit confirmation. | usability; exploratory; manual | No | Approved | v1.0
TC-DB-AUTH-001 | Verify salted password persistence | Confirm registration stores a one-way salted hash instead of the submitted password. | Database | Critical | NFR-SEC-001 | AC-US001-05 | A new temporary database is available. | Unique synthetic member and password | 1. Register a synthetic member. 2. Query the stored password value. 3. Compare it with the submitted password and another hash of the same password. | The stored value differs from the submitted password, verifies successfully, and differs from a separately generated salted hash. | database; security; regression | Yes | Approved | v1.0
TC-API-AUTH-001 | Reject an unauthenticated protected request | Confirm protected endpoints return 401 for missing or invalid bearer tokens. | API | Critical | FR-AUTH-003; NFR-SEC-001 | AC-US002-02 | The API is available. | No token; malformed token | 1. Request the profile endpoint without a token. 2. Repeat with an invalid token. | Each request returns 401 and no protected data. | api; auth; negative; regression | Yes | Approved | v1.0
TC-API-AUTHZ-001 | Reject update of another member's task | Confirm a member cannot update a task owned by another member. | API | Critical | FR-AUTHZ-001; NFR-SEC-001 | AC-US007-02 | Two members and one task owned by member one exist. | Member two token; member one task ID | 1. Record the task row. 2. Submit an update as member two. 3. Inspect the response and stored row. | The API returns 404 and the task row is unchanged. | api; authorization; negative; regression | Yes | Approved | v1.0
TC-API-AUTHZ-002 | Reject deletion of another member's task | Confirm a member cannot delete a task owned by another member. | API | Critical | FR-AUTHZ-001; NFR-SEC-001 | AC-US007-03 | Two members and one task owned by member one exist. | Member two token; member one task ID | 1. Record the task row count. 2. Submit delete as member two. 3. Inspect the response and stored row. | The API returns 404 and the task row remains present. | api; authorization; negative; regression | Yes | Approved | v1.0
TC-API-AUTHZ-003 | Reject unauthenticated task access | Confirm task endpoints reveal no data when the bearer token is absent or invalid. | API | Critical | FR-AUTHZ-001; NFR-SEC-001 | AC-US007-04 | At least one task exists. | No token; malformed token | 1. Request the task list without a token. 2. Repeat with an invalid token. | Each request returns 401 without task data. | api; authorization; negative; regression | Yes | Approved | v1.0
TC-DB-AUTHZ-001 | Verify denied mutations leave database unchanged | Confirm authorization failures do not change another member's task or row counts. | Database | Critical | FR-AUTHZ-001; NFR-SEC-001 | AC-US007-05 | Two members and one task owned by member one exist in a temporary database. | Member two token; member one task ID | 1. Snapshot the task row and count. 2. Attempt update and delete as member two. 3. Query the row and count again. | Values and counts are identical before and after both denied requests. | database; authorization; integrity; regression | Yes | Approved | v1.0
TC-RELEASE-001 | Validate Must-requirement traceability | Confirm each Must requirement links to an acceptance criterion and approved test case. | Management | Critical | BR-004 | AC-US010-01 | Phase 9 registers are present. | Requirements, criteria, cases, and traceability CSV files | 1. Parse requirement priorities. 2. Resolve acceptance and case links. 3. Report missing or duplicate IDs. | Every Must requirement has a resolvable path and all identifiers are unique. | release; traceability; quality-gate | Yes | Approved | v1.0
TC-RELEASE-002 | Apply the smoke quality gate | Confirm the critical smoke workflow passes before broader release testing. | Management | Critical | BR-004 | AC-US010-02 | The corrected baseline and browser are available. | Smoke marker | 1. Run the smoke marker. 2. Review the result and retained report. | All selected smoke tests pass; otherwise broader release testing stops. | release; smoke; quality-gate | Yes | Approved | v1.0
TC-RELEASE-003 | Apply the API quality gate | Confirm critical API contract and authorization coverage has no remaining failure. | Management | Critical | BR-004 | AC-US010-03 | The complete API cycle has executed. | CYCLE-PH6-API-20260810 | 1. Review planned, passed, failed, and blocked counts. 2. Review critical linked defects. | All 24 API tests pass and no critical contract or authorization defect is open. | release; api; quality-gate | Yes | Approved | v1.0
TC-RELEASE-004 | Apply the accessibility quality gate | Confirm accessibility results include manual evidence and no open critical finding. | Management | Critical | BR-003; BR-004 | AC-US010-04 | The Phase 8 assessment and retests are complete. | Automated, keyboard, Lighthouse, WAVE, and NVDA evidence | 1. Review the cycle result. 2. Confirm manual evidence is present. 3. Review open critical findings. | The dedicated suite passes, manual evidence is included, and no critical accessibility finding remains open. | release; accessibility; quality-gate | Yes | Approved | v1.0
TC-RELEASE-005 | Evaluate the local performance baseline | Confirm bounded performance observations are compared with NFR-PERF-001. | Performance | Medium | NFR-PERF-001; BR-004 | AC-US010-05 | Phase 10 environment and workload are approved. | Local response time, throughput, concurrency, and error-rate observations | 1. Run the approved local baseline. 2. Compare observations with the target. 3. Record environment and limitations. | The result reports all required measures without presenting local observations as production capacity. | release; performance; planned | Yes | Draft | v1.0
TC-RELEASE-006 | Produce the final release recommendation | Confirm all planned cycle results, defects, exceptions, and risks support a clear recommendation. | Management | Critical | BR-004 | AC-US010-06 | All planned project cycles are complete. | Cycle register, execution register, defects, risks, and accepted exceptions | 1. Reconcile final counts. 2. Review open defects and exceptions. 3. Record technical and stakeholder summaries. 4. State the recommendation. | The final summary is complete, internally consistent, and states Release, Conditional Release, or Do Not Release with reasons. | release; summary; planned | Partial | Draft | v1.0

## Defects
Defect ID | Summary | Source Cycle | Test Case ID | Severity | Priority | Owner Role | Status | Resolution | Retest Evidence
DEF-P3-001 | Form borders and focus indicator missed the component-contrast target | CYCLE-PH3-20260810 | TC-ACCESS-003 | Major | High | Frontend developer | Closed | Darkened borders and added a two-color focus treatment | PH3-20260810-034 passed; full Brave regression passed
DEF-P3-002 | The page overflowed horizontally at the 320-pixel target | CYCLE-PH3-20260810 | TC-COMPAT-001 | Major | High | Frontend developer | Closed | Removed the minimum-width constraint and corrected the narrow header | PH3-20260810-036 passed at all three widths; full Brave regression passed
DEF-P8-001 | Success feedback was not announced consistently by NVDA | CYCLE-PH8-ACCESSIBILITY-20260810 | TC-ACCESS-002 | Major | High | Frontend developer | Closed | Kept an atomic live region present before message updates | NVDA announced success and error feedback on retest
DEF-P8-002 | WAVE reported two implicit label-association alerts | CYCLE-PH8-ACCESSIBILITY-20260810 | TC-ACCESS-002 | Minor | Low | Frontend developer | Closed | Added explicit label and control associations | WAVE workspace retest reported zero alerts

## Summary
WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register
WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register | WorkBoard Phase 9 Management Register
Measure | Value |  | Checkpoint decision | Checkpoint decision | Checkpoint decision
Registered test cases | 49 |  | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete. | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete. | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete.
Registered cycles | 8 |  | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete. | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete. | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete.
Completed cycles | 6 |  | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete. | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete. | Continue to Phase 10 after Phase 9 approval. The six-test regression gate passed; final release readiness remains not evaluated until later planned cycles complete.
Execution records | 53
Failed attempts retained | 2 |  | Evidence boundary | Evidence boundary | Evidence boundary
Closed defects | 4 |  | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim. | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim. | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim.
Stories with end-to-end trace chains | 10 |  | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim. | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim. | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim.
|  |  | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim. | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim. | Results describe local execution with synthetic data. Performance and simulated UAT remain planned. Accessibility results are not a certification or legal-compliance claim.