## Scenario Results
Scenario ID | Test Case ID | UAT Criterion ID | Participant Role | Expected Result | Actual Result | Issue ID | Classification | Final Result | Execution ID
UAT-001 | TC-UAT-001 | UAT-AC-001 | Simulated operations coordinator | Member workspace opens with understandable identity and role. | Workspace opened and displayed the synthetic member identity and role. |  | None | Pass | PH11-20260810-001
UAT-002 | TC-UAT-002 | UAT-AC-002 | Simulated operations coordinator | Profile and normal task lifecycle persist with clear feedback. | Profile and task lifecycle completed; due dates and priority were requested as future behavior. | UAT-ENH-001 | Enhancement request | Pass | PH11-20260810-002
UAT-003 | TC-UAT-003 | UAT-AC-003 | Simulated operations coordinator | Search and state filters return only work matching both conditions. | Combined search and state filtering returned the expected personal tasks. |  | None | Pass | PH11-20260810-003
UAT-004 | TC-UAT-004 | UAT-AC-004 | Simulated operations coordinator | Refresh preserves the valid session without repeating a task action. | Session remained valid and the uniquely named task appeared exactly once. |  | None | Pass | PH11-20260810-004
UAT-005 | TC-UAT-005 | UAT-AC-005 | Simulated operations coordinator | Administrator identifies owners and cannot mutate another member's task. | Owner was visible and the team task had no mutation controls; initial reprioritization expectation was clarified. | UAT-OBS-001 | Requirement misunderstanding | Pass | PH11-20260810-005
UAT-006 | TC-UAT-006 | UAT-AC-006 | Simulated operations coordinator | Sign-out returns to sign-in and refresh does not reopen the workspace. | Sign-in remained displayed after sign-out and refresh. |  | None | Pass | PH11-20260810-006

## Traceability
Requirement ID | User Story ID | Acceptance Criterion ID | UAT Criterion ID | UAT Scenario ID | Test Case ID | Automated Replay | Execution ID | Issue ID | Retest Status | Final Status
FR-AUTH-001 | US-001 | AC-US001-01 | UAT-AC-001 | UAT-001 | TC-UAT-001 | tests/uat/test_uat_browser_replay.py::test_member_business_workflow_replay | PH11-20260810-001 |  | Not required | Accepted
FR-TASK-001; FR-TASK-003; FR-TASK-004; FR-TASK-005; FR-PROFILE-001 | US-003; US-005 | AC-US003-01; AC-US003-04; AC-US003-05; AC-US003-06; AC-US003-07; AC-US003-08; AC-US003-09; AC-US005-02; AC-US005-03 | UAT-AC-002 | UAT-002 | TC-UAT-002 | tests/uat/test_uat_browser_replay.py::test_member_business_workflow_replay | PH11-20260810-002 | UAT-ENH-001 | Not required | Accepted; enhancement deferred
FR-TASK-006 | US-004 | AC-US004-01; AC-US004-03; AC-US004-04; AC-US004-05; AC-US004-06 | UAT-AC-003 | UAT-003 | TC-UAT-003 | tests/uat/test_uat_browser_replay.py::test_member_business_workflow_replay | PH11-20260810-003 |  | Not required | Accepted
NFR-REL-001 | US-002; US-009 | AC-US002-04; AC-US009-01 | UAT-AC-004 | UAT-004 | TC-UAT-004 | tests/uat/test_uat_browser_replay.py::test_member_business_workflow_replay | PH11-20260810-004 |  | Not required | Accepted
FR-ADMIN-001; FR-ADMIN-002 | US-006 | AC-US006-01; AC-US006-02; AC-US006-05 | UAT-AC-005 | UAT-005 | TC-UAT-005 | tests/uat/test_uat_browser_replay.py::test_administrator_business_workflow_replay | PH11-20260810-005 | UAT-OBS-001 | Not required | Accepted; requirement clarified
FR-AUTH-003 | US-002 | AC-US002-01 | UAT-AC-006 | UAT-006 | TC-UAT-006 | tests/uat/test_uat_browser_replay.py::test_member_business_workflow_replay | PH11-20260810-006 |  | Not required | Accepted

## Summary
WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register
WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register | WorkBoard Phase 11 Simulated UAT Register
Measure | Value |  | Participation boundary | Participation boundary | Participation boundary
Planned scenarios | 6 |  | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off. | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off. | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off.
Passed | 6 |  | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off. | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off. | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off.
Failed | 0 |  | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off. | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off. | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off.
Blocked | 0 |  | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off. | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off. | Disclosed single-person role-play using a simulated operations-coordinator persona. No external client participated, and this workbook is not a real client sign-off.
Not run | 0
Confirmed defects | 0 |  | Decision boundary | Decision boundary | Decision boundary
Requirement misunderstandings | 1 |  | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated. | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated. | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated.
Enhancement requests | 1 |  | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated. | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated. | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated.
Acceptance decision | Accept with documented deferred enhancement |  | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated. | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated. | All six scenarios passed. UAT-OBS-001 is a clarified requirement misunderstanding; UAT-ENH-001 is a deferred enhancement. Final release readiness remains not evaluated.

## Issue Register
Issue ID | Scenario | Observation | Classification | Severity | Priority | Disposition | Retest Outcome
UAT-OBS-001 | UAT-005 | The participant initially expected team oversight to allow reprioritizing another member task. | Requirement misunderstanding | Not applicable | Low | Approved read-only scope clarified after the attempt. | Not required; approved behavior confirmed.
UAT-ENH-001 | UAT-002 | The participant requested due dates and priority values for personal tasks. | Enhancement request | Not applicable | Medium | Linked to deferred backlog item ENH-002 for future prioritization. | Not required unless the enhancement is approved and implemented.