## Summary
WorkBoard Phase 12 Remediation and Retest Register
Measure | Value | Scope boundary
Managed executions | 10 | Four genuine closed defects were independently confirmed, followed by six managed critical regression cases. Phase 11 contained no product defect, so no UAT observation was converted into remediation work.
Passed | 10
Failed | 0
Blocked | 0
Not run | 0
Closed defects confirmed | 4 | Count reconciliation
Focused automated checks | 12 | The managed cycle contains 10 cases. The focused command produces 12 automated checks because the responsive case expands to three viewport parameters.
Unauthorized product changes | 0
Complete project tests | 121
Frontend production build | PASS
Checkpoint decision | PASS

## Defect Retests
Defect ID | Severity | Source Case | Original Evidence | Original Result | Correction | Original Retest | Phase 12 Execution | Confirmation Method | Phase 12 Result | Final Status | Automated Checks
DEF-P3-001 | Major | TC-ACCESS-003 | PH3-20260810-033 | Fail | Darkened component borders and added a two-color focus treatment. | PH3-20260810-034: Pass | PH12-20260810-001 | Component and text contrast confirmation | Pass | Closed | 1
DEF-P3-002 | Major | TC-COMPAT-001 | PH3-20260810-035 | Fail | Removed the page minimum-width constraint and corrected the narrow header layout. | PH3-20260810-036: Pass | PH12-20260810-002 | Responsive checks at 320, 760, and 1,280 pixels | Pass | Closed | 3
DEF-P8-001 | Major | TC-ACCESS-002 | A11Y-004 and NVDA initial observation | Fail | Kept an atomic live region in the document before messages were populated. | NVDA and PH8-20260810-001: Pass | PH12-20260810-003 | Live-region role and atomicity confirmation | Pass | Closed | 1
DEF-P8-002 | Minor | TC-ACCESS-002 | A11Y-005 and WAVE initial observation | Fail | Added explicit label and control associations. | WAVE workspace retest: Pass | PH12-20260810-004 | Accessible-name and heading-order confirmation | Pass | Closed | 1

## Regression
Execution ID | Test Case ID | Risk Area | Automated Check | Actual Result | Final Result | Automated Checks
PH12-20260810-005 | TC-AUTH-004 | Authentication | test_incorrect_password_does_not_create_session | Incorrect credentials created no session. | Pass | 1
PH12-20260810-006 | TC-TASK-001 | Task lifecycle | test_member_task_lifecycle | The member task lifecycle completed successfully. | Pass | 1
PH12-20260810-007 | TC-TASK-002 | Validation feedback | test_blank_task_title_is_rejected | A blank task title was rejected with understandable feedback. | Pass | 1
PH12-20260810-008 | TC-SEARCH-006 | Search and filter | test_search_and_status_filter_apply_together | Search and state filters applied together. | Pass | 1
PH12-20260810-009 | TC-PROFILE-001 | Profile persistence | test_profile_name_persists_across_sessions | The updated display name persisted across sessions. | Pass | 1
PH12-20260810-010 | TC-ADMIN-002 | Administrator authorization | test_administrator_team_view_is_read_only_for_member_task | The administrator team view remained read-only for another member's task. | Pass | 1

## UAT Decisions
Issue ID | Classification | Approved Baseline | Product Change | Retest Required | Phase 12 Disposition
UAT-OBS-001 | Requirement misunderstanding | Administrator team oversight is read-only. | None | No | Approved behavior passed regression; this is not a defect retest.
UAT-ENH-001 | Enhancement request | Tasks do not include due dates or priority. | None | No | Linked to deferred ENH-002; change control would precede any future retest.